## Project schedule
| Ομάδα_5_Project | [5 empty] | Project start: | [7 empty] | 2024-04-07
| [ΠΛΗΠΡΟ - ΗΛΕ52] 2023 - 2024 | [5 empty] | Display week: | [7 empty] | 1
Ανάπτυξη scientific calculator με τη βιβλιοθήκη tkinter
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22 | [6 empty] | 2024-07-29
| ΣΤΟΧΟΙ | ΑΝΑΘΕΣΗ ΣΕ | ΠΡΟΟΔΟΣ | ΕΝΑΡΞΗ | ΛΗΞΗ | time axis 2024-04-08 to 2024-08-04
 | time axis 2024-04-08 to 2024-08-04
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Αρχική φάση
| Μελέτη του προβλήματος | Παναγιωτάκη | 100% | 2024-04-07 | 2024-04-30 | 24
| Συγκέντρωση υλικού | Παναγιωτάκη | 100% | 2024-04-07 | 2024-04-30 | 24
| Εμβάθυνση σε βιβλιοθήκες | Παναγιωτάκη | 100% | 2024-04-07 | 2024-04-30 | 24
| Καταγραφή λειτουργικότητας | Παναγιωτάκη | 100% | 2024-04-07 | 2024-04-30 | 24
| Σχεδιασμός διεπαφής χρήστη | Παναγιωτάκη | 100% | 2024-04-07 | 2024-04-30 | 24
Προγραμματισμός και σχεδίαση
| Υλοποίηση | Παναγιωτάκη | 100% | 2024-04-07 | 2024-05-30 | 54
| Έλεγχος ορθότητας | Παναγιωτάκη | 100% | 2024-04-07 | 2024-06-02 | 57
Τελική φάση
| Τεκμηρίωση λύσης | Παναγιωτάκη | 100% | 2024-04-30 | 2024-06-12 | 44
| Συγγραφή τελικού παραδοτέου | Παναγιωτάκη | 100% | 2024-04-30 | 2024-06-12 | 44
Προετοιμασία
| Συγγραφή ατομικής έκθεσης | Παναγιωτάκη | 0% | 2024-04-15 | 2024-06-12
| Συγγραφή ομαδικής έκθεσης | Παναγιωτάκη | 100% | 2024-04-15 | 2024-06-12
| Δημιουργία παρουσίασης (video) | Παναγιωτάκη | 100% | 2024-04-30 | 2024-06-12 | 44
Insert new rows ABOVE this one
Note on I11: Μελέτη του προβλήματος, επιλογή υλικού και τεχνικών υλοποίησης
Note on I12: Συγκέντρωση υλικού για το Project (tutorials, videos, web pages κλπ)
Note on I13: Συγκέντρωση των απαραίτητων βιβλιοθηκών για τη διεπαφή (tkinter)
Note on I14: Σύνταξη της πρώτης παρουσίασης λειτουργικότητας (Functionality 1.0)
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Δημιουργία παρουσίασης της διεπαφής χρήστη (PowerPoint) και μερική υλοποίηση της v. 1.0
Note on I16: Δημιουργία SmartCalc v.1.0 και SmartCalc v.1.0.1
Note on J16: Δημιουργία SmartCalc v.1.0.3
Note on J17: Bug fixing
Note on K19: Συγγραφή τεκμηρίωσης σε μορφή ιστοσελίδας (στην έκδοση 3.0 ) στα Αγγλικά
Note on L16: Shery: Δημιουργία SmartCalc 3.1 και executable αρχείου
Note on L17: Bug fixing
Note on L19: Συγγραφή τεκμηρίωσης σε μορφή ιστοσελίδας (στην έκδοση 3.0 θα προστεθεί κουμπί που θα ανοίγει το documentation)
Note on M16: Δημιουργία SmartCalc v.1.0.3
Note on M17: Bug fixing
Note on O14: Σύνταξη της δεύτερης παρουσίασης λειτουργικότητας (Functionality 2.0)
Note on P16: Δημιουργία SmartCalc v.1.0.4 και SmartCalc 2.0
Note on P17: Bug fixing
Note on P23: Έναρξη συγγραφής ομαδικής έκθεσης
Note on S16: Δημιουργία SmartCalc 2.0.3
Note on W16: Δημιουργία SmartCalc 2.0.4
Note on AA16: Shery: Δημιουργία SmartCalc 2.0.5 και executable αρχείου
Note on AF16: Shery: Δημιουργία SmartCalc 3.0 και executable αρχείου
Note on AF24: Έναρξη συγκέντρωσης υλικού για την video παρουσίαση
Note on AU16: Shery: Δημιουργία SmartCalc 3.1 και executable αρχείου
Note on AU17: Bug fixing
Note on AX16: Shery: Δημιουργία SmartCalc 3.2
Note on AX17: Bug fixing
Note on AY16: Shery: Δημιουργία SmartCalc 3.3
Note on AY17: Bug fixing
Note on BB16: Shery: Δημιουργία SmartCalc 3.4
Note on BB17: Bug fixing
Note on BC17: Bug fixing
Note on BD17: Bug fixing
Note on BJ17: Bug fixing

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.